## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Deep Learning - Bird Image Recognition Project
Henallux Pierrard |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Nell Guissard (& Antoine Z)
Project Start Date: | 2025-04-03 |  |  |  |  | April | [27 empty] | May
Scrolling Increment: | 0 | time axis 2025-04-03 to 2025-05-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-04-03 to 2025-05-28
Milestones
Analysis | Milestone | Nell & Antoine | 0% | 2025-04-03 | 7 | bar: 2025-04-03 to 2025-04-09
Realisation | Milestone | Nell & Antoine | 0% | 2025-04-10 | 21 | bar: 2025-04-10 to 2025-04-30
Verifying & Testing | Milestone | Nell & Antoine | 0% | 2025-05-01 | 7 | bar: 2025-05-01 to 2025-05-07
Presentation | Milestone | Nell & Antoine | 0% | 2025-05-08 | 7 | bar: 2025-05-08 to 2025-05-14
Final Report | Milestone | Nell & Antoine | 0% | 2025-05-15 | 7 | bar: 2025-05-15 to 2025-05-21
Realisation
Select Dataset | Med Risk | Nell & Antoine | 0% | 2025-04-10 | 7
Python Programming | High Risk | Nell & Antoine | 0% | 2025-04-10 | 14
Model Training and Testing | Med Risk | Nell & Antoine | 0% | 2025-04-10 | 14
Model Optimizing | Low Risk | Nell & Antoine | 0% | 2025-04-24 | 7
Implement Image Capture and Processing | Low Risk | Nell & Antoine | 0% | 2025-04-24 | 7
Data Base Building | Med Risk | Nell & Antoine | 0% | 2025-04-24 | 7
Develop Visualization | High Risk | Nell & Antoine | 0% | 2025-04-24 | 7
Testing and Verifying
Field Testing and Improvements | Goal | Nell & Antoine | 0% | 2025-05-15 | 7 | 2025-05-15: 2; 2025-05-16: 2; 2025-05-17: 2; 2025-05-18: 2; 2025-05-19: 2; 2025-05-20: 2; 2025-05-21: 2
Presentation
PowerPoint Preparation | Milestone | Nell & Antoine | 0% | 2025-05-08 | 7 | bar: 2025-05-08 to 2025-05-14
Presentation Training | Milestone | Nell & Antoine | 0% | 2025-05-08 | 7 | bar: 2025-05-08 to 2025-05-14
Documentation - Report
Report Writing (LaTeX ?) | High Risk | Nell & Antoine | 0% | 2025-05-15 | 7
Report Correcting | Med Risk | Nell & Antoine | 0% | 2025-05-15 | 7
To add more data, Insert new rows ABOVE this one